**Academic Program Review Process and Timeline**

**Programs with Consultant Review (7-year cycle)**

[Self-Study report is due June 1 in year t. If on the 2026-2027 cycle, year t = 2026.]

[Consultant reviews to be completed in the fall semester, year t]

[APR reviews to be completed in the spring semester, year (t+1)]

[Review reported to System in June, year (t+1)]

|  |  |  |  |
| --- | --- | --- | --- |
| **Step** | **Responsible Party** | **Actions Required** | **Dates/Deadlines** |
| 1 | Provost’s Office | Unit/Department/Program (U/D/P) is notified that its program self-study will be reviewed in 3 years. A list of recommendations that need to be addressed by the program, per the past APR report, will be sent to the U/D/P.  | June 1, t-3 |
| 2 | U/D/P | U/D/P submit an assessment report to the University Program Assessment Committee at two timepoints as they move towards the completion of their APR self-study. | t-5t-2 |
| 3 | Provost’s Office & U/D/P | Recommended that U/D/P representative attends APR Self Study Information Session sponsored by the Provost’s Office. | January, year t-1 or t |
| 4 | Provost’s Office | U/D/P is notified that its program will be reviewed by APR in the upcoming year, with self-study report due on June 1, year t. U/D/P is provided with relevant materials for the self-study report.  | January, year t-1 |
| 5 | U/D/P | Identification of external consultant(s) and submission to dean for approval. | March 1, year t |
| 6 | Dean | Approval of the external consultant(s). | May 1, year t |
| 7 | Institutional Research | Institutional Research prepares the Unit Data Sheet and posts on Academic Program Review Canvas site. | January 1, year t |
| 8 | U/D/P | U/D/P submits completed APR Self-Study to the Dean. | June 1, year t  |
| 9 | Dean | Review of APR Self-Study for completeness. One month is allowed for reports identified as incomplete or insufficient to be completed. | July  |
| 10 | U/D/P | External consultant visits campus. The consultant campus visit is made after the start of the fall semester. External consultant completes consultant’s report and makes recommendations. | September |
| 11 | U/D/P | U/D/P puts final package together including the APR Self-Study, consultant’s report, and the U/D/P’s response to the consultant’s report and posts on the APR Canvas site. U/D/P chair or their designated representative, APR administrative consultants, and APR members will be granted electronic access to APR Canvas site. | November |
| 12 | Dean | Dean reviews the final package and prepares a summary including recommendations. Posts letter on APR Canvas site. | December |
| 13 | GEL Dean | ***Only for graduate program reviews*** Dean of Graduate and Extended Learning reviews the final package and prepares a summary including recommendations. Posts letter on APR Canvas site. | January  |
| 14 | UG/Grad APR Committee | UG/Grad APR Committee forms sub-committee to review completed self-study. | January |
| 15 | UG/Grad APR Committee | APR sub-committee reviews completed materials, meets with U/D/P representative, presents APR Report to full UG/Grad APR committee. Committee reviews and approves report.  | March 1, year (t+1) |
| 16 | UG/Grad APR Committee Chair | APR Report submitted in pdf form to the Faculty Senate for review and acceptance. (If review indicates a 3 year progress report is required, see 3 year review process and timeline.) | April 1 |
| 17 | Faculty Senate Chair | Faculty Senate forwards accepted report to Provost/Vice Chancellor. | May |
| 18 | Provost’s Office | Provost/Vice Chancellor reviews report and responds to the Dean and U/D/P. | May |
| 19 | Provost’s Office | Completion of program review is reported to System. | June 1 |

**Three-Year APR Progress Report Process and Timeline**

If Faculty Senate requests a three-year follow-up report, the report will be due in February - 3 calendar years after the senate decision.

|  |  |  |  |
| --- | --- | --- | --- |
| **Step** | **Responsible Party** | **Actions Required** | **Dates/Deadlines** |
| 1 | Provost’s Office | Unit/Department/Program (U/D/P) is notified that its 3 year progress report is due in February. A list of recommendations that need to be addressed by the program, per the past APR report, will be sent to the U/D/P along with relevant materials to complete the progress report. | September |
| 2 | U/D/P | U/D/P completes 3-year progress report and posts it on APR Canvas site.  | February 1st |
| 3 | UG/Grad APR Committee | UG/Grad APR committee reviews the 3-year progress report and reports to the U/D/P, along with the Dean, Faculty Senate, and Provost, if the program has made 1) acceptable progress, 2) minimal progress or 3) unacceptable progress. A brief justification for decision is included in the report.  | March |
| 4 | Provost’s Office | Provost reviews report, consults with Dean, and responds to U/D/P (response copied to Dean, Faculty Senate, APR committee)  | April |